## README
Freshservice Implementation Checklist
A comprehensive, phase-by-phase checklist for Freshservice implementation professionals
How to Use This Checklist
How to Use | Work through each tab in order. Check off items as completed. Use the Status column to track progress.
Tabs | Each tab = a major implementation phase. Phases align with the book 'Freshservice: From Kickoff to Hypercare'.
Status Key | ✅ Complete ¦ 🔄 In Progress ¦ ⏳ Not Started ¦ ⛔ Blocked ¦ N/A – Not Applicable
Priority Key | 🔴 Critical ¦ 🟡 High ¦ 🟢 Standard
Notes | Use the Notes column to capture decisions, owners, dependencies, or links to documentation.
Source | Based on: 'Mastering Freshservice Implementations' and 'Freshservice: From Kickoff to Hypercare' by Race P. Vanderdecken, plus Freshservice platform knowledge.
Status Key – Visual Reference
Status | Meaning / When to Use
✅ Complete | Task is fully done, tested, and verified. No further action needed.
🔄 In Progress | Work has started but is not yet finished. Assign an owner and target date.
⏳ Not Started | Default state. Task has not been started yet.
⛔ Blocked | Cannot proceed due to a dependency, missing access, or external blocker. Log in RAID.
N/A | This item does not apply to this implementation. Document reason in Notes.
Checklist Tabs Overview
1 – Pre-Implementation | Kickoff, discovery, requirements, project governance
2 – Instance Setup | Account provisioning, admin access, security, branding, sandbox
3 – User & Access Mgmt | Agents, requesters, roles, groups, departments, locations
4 – Core Ticketing | Email channels, SLAs, business hours, custom fields, ticket forms
5 – Service Catalog | Categories, catalog items, approval workflows, visibility rules
6 – Automation | Workflow Automator, Business Rules, Supervisor Rules, Scheduler
7 – ITSM Modules | Incident, Problem, Change, Release management configuration
8 – Asset & CMDB | Asset types, CMDB, discovery, software/contract/vendor management
9 – AI & Channels | Freddy AI, chatbot, Microsoft Teams / Slack integration, portal
10 – Knowledge & Reporting | Knowledge base, solution articles, reports, dashboards
11 – Go-Live & Hypercare | UAT, training, go-live, post-implementation review, handoff

## 1 – Pre-Implementation
Freshservice Implementation – 1 – Pre-Implementation
# | Priority | Task / Action Item | Status | Notes / Owner
1.1 Project Kick-Off
1 | 🔴 | Schedule and host formal kickoff call with all key stakeholders (IT leads, process owners, exec sponsors) | ⏳ Not Started | Confirm attendees, send calendar invite with agenda
2 | 🔴 | Distribute and review signed Statement of Work (SOW) with all parties | ⏳ Not Started | Ensure scope, exclusions, and milestones are acknowledged
3 | 🔴 | Introduce ITIL/ITSM framework to stakeholders; align on terminology (Incident, Problem, Change, etc.) | ⏳ Not Started | Frame the engagement as ITSM transformation, not just tool setup
4 | 🟡 | Present the implementation roadmap with key milestones and phases | ⏳ Not Started | Include estimated dates; tie to SOW deliverables
5 | 🟡 | Introduce and share RAID log (Risks, Assumptions, Issues, Dependencies) | ⏳ Not Started | Use shared spreadsheet; assign initial RAID entries
6 | 🟡 | Establish communication cadence – weekly meeting schedule, escalation path, and stakeholder register | ⏳ Not Started | Book recurring weekly call; identify project manager on each side
7 | 🟢 | Confirm test strategy: sandbox, staging, or direct production configuration | ⏳ Not Started | Document decision; note sandbox licensing requirements
8 | 🟢 | Introduce Freddy AI capabilities and set expectations for AI-assisted service delivery | ⏳ Not Started | Confirm which Freddy modules are in scope (Copilot, Insights, Agent)
1.2 Discovery & Requirements Gathering
9 | 🔴 | Schedule and conduct discovery workshops with all departments that will use Freshservice (IT, HR, Facilities, Finance, etc.) | ⏳ Not Started | Separate sessions per department; document attendees and outputs
10 | 🔴 | Document current-state ticket intake methods (email, phone, portal, walk-up, Slack, etc.) | ⏳ Not Started | List all inbound channels; note which will be migrated
11 | 🔴 | Map current escalation paths, response expectations, and SLA commitments | ⏳ Not Started | Capture tiered support structure (Tier 1/2/3)
12 | 🔴 | Capture ticketing requirements: categories, priorities, statuses, custom fields needed | ⏳ Not Started | Build a configuration workbook from this session
13 | 🟡 | Identify service catalog candidates (ask each dept to list services they provide to employees) | ⏳ Not Started | Target 25–30 items for initial launch; document owner per item
14 | 🟡 | Document approval workflows: who approves what, under what conditions, fallback behavior | ⏳ Not Started | Note cost thresholds, manager lookups, CAB requirements
15 | 🟡 | Gather reporting & dashboard requirements from IT managers and executives | ⏳ Not Started | Note key KPIs: SLA compliance, resolution time, ticket volume by type
16 | 🟡 | Review legacy system exports, existing forms, and email-driven workflows | ⏳ Not Started | Use these to guide category design and migration decisions
17 | 🟡 | Identify integration requirements: AD/Azure AD, HRIS, Jira, Slack, Teams, monitoring tools, etc. | ⏳ Not Started | Prioritize integrations that impact go-live scope
18 | 🟢 | Identify candidate knowledge base articles from existing documentation or FAQs | ⏳ Not Started | Review shared drives, wikis, or mailbox templates
19 | 🟢 | Determine asset management scope: what assets to track, discovery method, import sources | ⏳ Not Started | Confirm CMDB depth and initial asset import approach
20 | 🟢 | Define a Phase 2 backlog for enhancements not required on day one | ⏳ Not Started | Document in a separate tab or backlog tracker
1.3 Project Governance
21 | 🔴 | Establish recurring weekly status meetings (30–45 min) with fixed agenda | ⏳ Not Started | Agenda: task progress, RAID review, upcoming milestones, blockers
22 | 🟡 | Maintain and distribute meeting minutes and action items after each session | ⏳ Not Started | Assign owners and due dates for every action item
23 | 🟡 | Maintain RAID log throughout the project; review at every weekly meeting | ⏳ Not Started | Escalate high-priority risks immediately
24 | 🟢 | Document all implementation decisions in a configuration workbook or wiki | ⏳ Not Started | This becomes the source of truth for the configuration

## 2 – Instance Setup
Freshservice Implementation – 2 – Instance Setup
# | Priority | Task / Action Item | Status | Notes / Owner
2.1 Account Provisioning & Access
1 | 🔴 | Confirm Freshservice instance has been provisioned and URL is accessible (e.g., yourcompany.freshservice.com) | ✅ Complete | Verify with Freshworks or partner; share URL with project team
2 | 🔴 | Log in as administrator and validate access to Admin Console, Workflow Automator, and all key modules | ✅ Complete | Test role visibility; note any missing features vs. licensed plan
3 | 🔴 | Review Admin > Account > Plans & Billing – confirm plan tier (Starter / Growth / Pro / Enterprise) | ✅ Complete | Document which features are included and which are excluded
4 | 🟡 | Invite implementation team members as Admins or Occasional Agents as appropriate | ✅ Complete | Use Agents > Invite Team sparingly; track license usage
5 | 🟡 | Enable a 'Under Construction – Not Yet Live' login banner if the portal is publicly accessible during setup | ✅ Complete | Prevents premature end-user submissions
6 | 🟢 | Decide on account mode: Employee Support Mode vs. Managed Services Mode | ✅ Complete | MSP or multi-client = Managed Services; internal IT = Employee Support
2.2 General & Account Settings
7 | 🔴 | Set company name, administrator email, phone, and billing contact in Account Settings | ✅ Complete | Admin > Global Settings > Account Settings > Contact Details
8 | 🔴 | Configure primary time zone to match headquarters / primary support region | ✅ Complete | Critical for SLA accuracy; confirm with project sponsor
9 | 🔴 | Configure Business Hours (standard support hours, public holidays, exceptions) | 🔄 In Progress | Admin > Global Settings > Business Hours; create multiple schedules if needed
10 | 🟡 | Set date format, time format (12h/24h), and currency to match organizational standards | ✅ Complete | Admin > Global Settings > Service Desk Rebranding > Service Desk Settings
11 | 🟡 | Set the starting Ticket ID number (especially critical when migrating from another system) | ⏳ Not Started | Avoid numbering conflicts with legacy ticket data
12 | 🟢 | Configure primary language and add any additional supported languages | 🔄 In Progress | Manage Languages option in Rebranding Settings
2.3 Security Settings
13 | 🔴 | Enable SSO integration with identity provider (Okta, Azure AD, Google Workspace, etc.) | ⏳ Not Started | Admin > Global Settings > Service Desk Security > Default Login Policy
14 | 🔴 | Configure SPF and DKIM DNS records for the support email domain | ⏳ Not Started | Admin > Global Settings > Service Desk Security > Email Security
15 | 🟡 | Enable Two-Factor Authentication (2FA) for all admin accounts | ⏳ Not Started | Redirects to myFreshworks.com; requires DNS/admin coordination
16 | 🟡 | Define IP range restrictions if access should be limited to corporate network / VPN | ⏳ Not Started | Enter allowed IP ranges; test before enforcing
17 | 🟡 | Set session timeout policy for inactivity auto-logout | ⏳ Not Started | Balance security with usability for agents
18 | 🟡 | Configure allowed and blocked attachment file types for ticket submissions | ⏳ Not Started | Block .exe, .bat, .js etc.; allow .pdf, .docx, .jpg, .png
19 | 🟢 | Enable Admin Notifications for security-sensitive changes (new agents, role updates) | ⏳ Not Started | Assign designated admins to receive alerts
20 | 🟢 | Configure public URL authentication settings (require login to view shared tickets/articles) | ⏳ Not Started | Determines visibility of public links to external users
2.4 Branding & Portal Identity
21 | 🔴 | Upload company logo to agent portal and requester portal | 🔄 In Progress | Admin > Global Settings > Service Desk Rebranding
22 | 🔴 | Set portal/service desk name as it will appear in notifications, headers, and emails | ⏳ Not Started | Use official brand name; confirm with marketing/communications
23 | 🟡 | Customize requester portal: background image, hero banner text, homepage cards | 🔄 In Progress | Configure cards: Browse Help Articles, Report Issue, Request Service, Approve Requests
24 | 🟡 | Customize agent portal color scheme to match corporate brand | 🔄 In Progress | Set left-menu color; upload agent portal logo
25 | 🟡 | Configure custom subdomain URL (e.g., support.yourcompany.com) – contact Freshservice support if needed | ⏳ Not Started | Note: requires DNS change and Freshservice support coordination
26 | 🟢 | Add support phone number to portal display | ⏳ Not Started | Prominent placement helps users contact support directly
27 | 🟢 | Back up any custom HTML/CSS before making portal branding changes | ⏳ Not Started | No built-in undo; store backups in a shared drive
2.5 Workspace Configuration
28 | 🔴 | Plan workspace structure: which departments need separate workspaces (IT, HR, Finance, Facilities, etc.) | ⏳ Not Started | Each workspace gets own workflows, SLAs, catalogs, and forms
29 | 🔴 | Create required workspaces using appropriate templates (IT, HR, Facilities, Finance, Legal, etc.) | ⏳ Not Started | Admin > Global Settings > Manage Workspaces; use blank for custom needs
30 | 🟡 | Assign IT Agent licenses to IT staff and Business Agent licenses to non-IT workspace agents | ⏳ Not Started | Confirm license types and quantities with Plans & Billing
31 | 🟡 | Configure workspace-specific ticket prefixes (#INC for IT, #CASE or #REQ for business workspaces) | ⏳ Not Started | Helps with routing clarity and user communication
32 | 🟢 | Review and document workspace agent assignments and permissions matrix | 🔄 In Progress | Capture in a role-permission spreadsheet for governance
2.6 Sandbox Environment
33 | 🟡 | Determine if Sandbox is included in the plan; contact Freshworks to activate if needed | ⏳ Not Started | Sandbox 2.0 offers perpetual existence and bi-directional sync
34 | 🟡 | Create sandbox instance and document the sandbox URL (yourcompany-sandbox.freshservice.com) | ⏳ Not Started | Restrict access to admins and implementation team only
35 | 🟡 | Configure selective module synchronization between sandbox and production using Config Sets | ⏳ Not Started | Test workflows, automations, and integrations in sandbox first
36 | 🟢 | Define sandbox refresh and promotion process (who approves changes moving to production) | ⏳ Not Started | Document as part of change management / governance policy

## 3 – User & Access Mgmt
Freshservice Implementation – 3 – User & Access Mgmt
# | Priority | Task / Action Item | Status | Notes / Owner
3.1 Agent Setup
1 | 🔴 | Determine agent import method: manual entry, CSV import, or directory sync (Azure AD, LDAP, Google Workspace) | ⏳ Not Started | For large teams, CSV or directory sync is strongly preferred
2 | 🔴 | Import or create all agent accounts with name, email, role, and group assignment | ⏳ Not Started | Verify license count before bulk import
3 | 🔴 | Assign appropriate roles to each agent (Agent, Supervisor, IT Agent, Business Agent, Admin) | ⏳ Not Started | Use least-privilege principle; avoid over-assigning Admin
4 | 🟡 | Configure and test Single Sign-On (SSO) for agents; disable password login if SSO is the standard | ⏳ Not Started | Verify SSO works before removing fallback password login
5 | 🟡 | Test 5–10 agent accounts across different role types to validate visibility and ticket behavior | ⏳ Not Started | Create test tickets and verify each role sees what it should
3.2 Requester (End-User) Setup
6 | 🔴 | Determine requester population source: CSV import, directory sync, or self-registration | ⏳ Not Started | Confirm with IT security whether self-registration is permitted
7 | 🔴 | Import or sync requester records with: name, email, department, location, manager | ⏳ Not Started | Accurate metadata powers automation, routing, and catalog visibility
8 | 🟡 | Validate that requester department and location fields are correctly populated post-import | ⏳ Not Started | Spot-check 10–20 records from different departments
9 | 🟢 | Configure requester self-registration settings and domain restrictions if applicable | ⏳ Not Started | Limit registration to approved email domains for security
3.3 Roles & Permissions
10 | 🔴 | Review all default system roles: Agent, Supervisor, Administrator, Occasional Agent | ⏳ Not Started | Understand default permissions before creating custom roles
11 | 🔴 | Identify any need for custom roles (e.g., 'CAB Approver', 'Read-Only Analyst', 'Tier 1 – IT Support') | ⏳ Not Started | Clone existing role; customize module-level permissions
12 | 🟡 | For each custom role, configure module permissions: Incident, CMDB, Workflow Automator, Change, KB, Reports | ⏳ Not Started | Align with ITIL least-privilege principle
13 | 🟡 | Assign Freshservice workspace-specific roles for agents working across multiple workspaces | ⏳ Not Started | An agent can have different roles in different workspaces
14 | 🟡 | Create and maintain a Role-Permission Matrix document listing every agent and their assigned role | ⏳ Not Started | Essential for audits, onboarding, and compliance
15 | 🟢 | Confirm Freddy AI access is granted only to agents whose roles require it (Copilot panels, Insights) | ⏳ Not Started | Review role definition to include/exclude Freddy widgets
16 | 🟢 | Schedule quarterly review of role assignments as team changes occur | ⏳ Not Started | Add to recurring IT governance calendar
3.4 Groups (Agent Teams)
17 | 🔴 | Define all agent groups based on function, department, or region (e.g., 'IT Helpdesk', 'HR Services', 'EMEA Support') | 🔄 In Progress | Groups drive ticket routing; name them clearly and consistently
18 | 🔴 | Create groups in Freshservice and add appropriate agents as members | ⏳ Not Started | Admin > [Workspace] > Groups
19 | 🔴 | Assign a Group Manager to each group; manager can approve, escalate, and monitor group performance | ⏳ Not Started | Confirm manager names with department leads
20 | 🟡 | Configure group auto-assignment: round-robin or load-balanced routing for each group | ⏳ Not Started | Check availability vs. load-balancing based on team size
21 | 🟡 | Set group-specific business hours if a group operates outside global hours (e.g., regional support team) | ⏳ Not Started | Tie group business hours to SLA policies
22 | 🟢 | Configure email notifications so the group is alerted when new tickets arrive | ⏳ Not Started | Avoid over-notifying; match notification settings to group needs
23 | 🟢 | Implement skills-based routing workaround: create 'Skill' custom fields on tickets and use Workflow Automator to route to correct group | ⏳ Not Started | Freshservice does not have native skills-based routing out-of-the-box
3.5 Departments & Locations
24 | 🔴 | Create all organizational departments in Freshservice using standardized names | ⏳ Not Started | Admin > Global Settings > Departments; align with HR system naming
25 | 🔴 | Create all locations (offices, remote tags, regional identifiers) | ⏳ Not Started | Admin > Global Settings > Locations; use consistent naming
26 | 🟡 | Assign all requesters to correct department and location (via CSV import or directory sync) | ⏳ Not Started | Departments and locations drive catalog visibility and SLA routing
27 | 🟡 | Test that automation rules, catalog visibility, and SLA policies trigger correctly based on department/location metadata | ⏳ Not Started | Create a test user per department and validate routing
28 | 🟢 | Standardize naming conventions (avoid 'HR' vs. 'Human Resources' duplicates in reports) | ⏳ Not Started | Document naming standards in configuration workbook
3.6 Requester Groups
29 | 🟡 | Create requester groups for users who share common access to catalog items or portals | ⏳ Not Started | Examples: 'Executives', 'New Hires', 'Contractors', 'VIP Users'
30 | 🟡 | Configure catalog item visibility rules using requester groups | ⏳ Not Started | Ensure VIPs or new hires see only relevant service items
31 | 🟢 | Define auto-membership rules for requester groups where applicable (e.g., by department) | ⏳ Not Started | Reduces manual maintenance of group membership

## 4 – Core Ticketing
Freshservice Implementation – 4 – Core Ticketing
# | Priority | Task / Action Item | Status | Notes / Owner
4.1 Email Channels & Mailboxes
1 | 🔴 | Add all organizational support email addresses to Freshservice (e.g., it@co.com, hr@co.com, facilities@co.com) | ⏳ Not Started | Admin > [Workspace] > Channels > Email
2 | 🔴 | Configure email forwarding from each mail provider (Outlook, Gmail) to the Freshservice address | ⏳ Not Started | Create forwarding rules or aliases in the mail server
3 | 🔴 | Verify SPF and DKIM records are published for each custom email domain | ⏳ Not Started | Prevents outgoing Freshservice emails from being flagged as spam
4 | 🟡 | Customize email notification templates for key lifecycle events: new ticket, reply, resolved, closed, survey | ⏳ Not Started | Admin > [Workspace] > Email Notifications; add branding, logo, and personalization tags
5 | 🟡 | Test end-to-end email flow: send from external account → ticket created → agent replies → user receives email | ⏳ Not Started | Test CC handling, attachments, and email threading
6 | 🟡 | Configure reply-to name and email footer to match organizational communication standards | ⏳ Not Started | Ensure users receive replies from a recognizable address
7 | 🟢 | Add email disclaimer or confidentiality notice to templates if required by policy or regulation | ⏳ Not Started | Legal may require this; confirm before go-live
8 | 🟢 | Test email behavior with CC, BCC, forwarded messages, and attachment sizes | ⏳ Not Started | Verify the 40 MB attachment limit per reply is understood by agents
4.2 SLA & OLA Policies
9 | 🔴 | Define and create all SLA policies including response and resolution targets by priority (Urgent/High/Medium/Low) | 🔄 In Progress | Base targets on discovery session commitments; align with business expectations
10 | 🔴 | Associate SLA policies with business hours schedules to ensure accurate SLA timer behavior | 🔄 In Progress | SLA timers must pause outside business hours if that is the intent
11 | 🔴 | Configure SLA escalation actions: who is notified on first, second, and final breach? | ⏳ Not Started | Set escalation emails/assignments for each SLA tier
12 | 🟡 | Create workspace-specific SLA policies where departments have different response commitments | ⏳ Not Started | IT vs. HR vs. Facilities often have different SLA windows
13 | 🟡 | Define OLA (Operational Level Agreement) policies for internal team performance tracking | ⏳ Not Started | OLAs are internal; SLAs are customer-facing
14 | 🟢 | Document all SLA commitments in a shared SLA register and share with stakeholders for sign-off | ⏳ Not Started | Prevents disputes about expectations after go-live
4.3 Ticket Properties & Custom Fields
15 | 🔴 | Define ticket categories, sub-categories, and items for the IT workspace | ⏳ Not Started | Drives reporting accuracy; align with real support patterns from discovery
16 | 🔴 | Configure ticket priority levels and the Priority Matrix (Impact + Urgency = Priority) | ⏳ Not Started | Admin > [Workspace] > Priority Matrix; align with ITIL priority calculation
17 | 🔴 | Create all required custom fields for tickets (type, placement, visibility, mandatory/optional) | ⏳ Not Started | Admin > [Workspace] > Field Manager; use dropdowns for consistent reporting
18 | 🟡 | Configure custom statuses beyond default (e.g., 'Pending Vendor', 'Awaiting Customer', 'In Review') | ✅ Complete | Admin > [Workspace] > Ticket Statuses
19 | 🟡 | Configure closure rules (mandatory resolution note, survey trigger, auto-close after X days pending) | ⏳ Not Started | Admin > [Workspace] > Closure Rules
20 | 🟡 | Set up ticket tags for additional filtering and automation | ⏳ Not Started | Keep tags standardized; document approved tag list
21 | 🟢 | Review and configure all ticket source types relevant to the organization | ⏳ Not Started | Default: Email, Portal, Phone, Chat; add Walk-up, Teams Bot, etc. as needed
22 | 🟢 | Configure planned start/end date and planned effort fields if used for scheduling | ⏳ Not Started | Useful for project-based or scheduled maintenance tickets
4.4 Ticket Views & Canned Responses
23 | 🟡 | Create shared ticket views for common agent workflows (e.g., 'My Open Tickets', 'SLA Breaching Soon', 'Unassigned') | ⏳ Not Started | Views reduce daily triage time; share relevant views with groups
24 | 🟡 | Build a library of canned responses for the top 10–20 most common reply types | ⏳ Not Started | Admin > [Workspace] > Canned Responses; use variables for personalization
25 | 🟢 | Create document templates for common response documents (e.g., approved change notification) | ⏳ Not Started | Admin > [Workspace] > Document Templates
4.5 Satisfaction Surveys
26 | 🟡 | Enable customer satisfaction (CSAT) surveys and configure trigger conditions (resolved/closed ticket) | ⏳ Not Started | Admin > [Workspace] > Satisfaction Surveys
27 | 🟡 | Customize survey questions, rating scale, and follow-up options | ⏳ Not Started | Keep surveys short; 1–3 questions maximum
28 | 🟢 | Configure survey notification email template and set delay before sending | ⏳ Not Started | Recommend sending 1–2 days after ticket resolution

## 5 – Service Catalog
Freshservice Implementation – 5 – Service Catalog
# | Priority | Task / Action Item | Status | Notes / Owner
5.1 Catalog Structure & Categories
1 | 🔴 | Define service catalog categories (max 10 for initial launch) based on discovery outputs | ✅ Complete | Examples: Hardware, Software, Access, HR Services, Facilities, Onboarding
2 | 🔴 | Create catalog categories and subcategories in Freshservice | ✅ Complete | Admin > Service Catalog; use consistent naming and intuitive icons
3 | 🟡 | Plan catalog item prioritization: focus on high-volume, high-value items first (max 25–30 items at launch) | ⏳ Not Started | Use request volume data from discovery to prioritize
4 | 🟡 | Assign a catalog owner to each service item for ongoing maintenance and approval | ⏳ Not Started | Document owner in configuration workbook
5.2 Catalog Item Configuration
5 | 🔴 | Create each catalog item with: name, description, category, icon, and fulfillment group | ⏳ Not Started | Use plain language in names (e.g., 'Request Laptop' not 'IT Provisioning Form')
6 | 🔴 | Add all required form fields to each catalog item (text, dropdown, checkbox, date, conditional) | ⏳ Not Started | Match fields to discovery requirements; use consistent naming
7 | 🔴 | Set field properties: mandatory vs. optional, agent-only vs. requester-visible | ⏳ Not Started | Only require fields that are truly needed to avoid form abandonment
8 | 🟡 | Configure conditional / dependent fields (show 'License Type' only if 'Software' is selected) | ⏳ Not Started | Reduces form complexity for users; improves data quality
9 | 🟡 | Configure visibility rules per catalog item: restrict by department, requester group, role, or location | ⏳ Not Started | Example: 'New Hire Kit' visible only to managers; 'VPN Access' hidden from contractors
10 | 🟡 | Link relevant knowledge base articles or FAQs to catalog items | ⏳ Not Started | Deflects unnecessary requests; improves user self-service
11 | 🟢 | Add help text, tooltips, and section headers to complex forms | ⏳ Not Started | Reduces agent follow-up and clarification requests
12 | 🟢 | Set default field values where appropriate to reduce user effort | ⏳ Not Started | Example: pre-fill 'Department' from requester's profile
5.3 Approval Workflows
13 | 🔴 | Identify which catalog items require approval before fulfillment | ⏳ Not Started | Common triggers: cost threshold, software access, contractor requests
14 | 🔴 | Configure inline approval logic for each applicable catalog item (approver, fallback, timeout behavior) | ⏳ Not Started | Freshservice supports manager lookup, static approver, or group approval
15 | 🟡 | Define fallback behavior for non-response: auto-approve after X days or escalate to manager's manager | ⏳ Not Started | Document policy and configure appropriately
16 | 🟡 | For complex conditional approvals, plan for Workflow Automator-based approval routing | ⏳ Not Started | Multi-level or branching approvals should use Workflow Automator
17 | 🟢 | Test all approval flows end-to-end using test accounts (requester → approver → fulfillment team) | ⏳ Not Started | Verify emails, task creation, and status transitions work correctly
5.4 Service Catalog Testing & Launch
18 | 🔴 | Impersonate different requester profiles and submit test requests for each catalog item | ⏳ Not Started | Validate: field behavior, approval routing, task creation, email notifications, visibility rules
19 | 🔴 | Validate that each item routes to the correct fulfillment group with correct SLA applied | ⏳ Not Started | Spot-check using the ticket activity log
20 | 🟡 | Conduct a stakeholder walkthrough of the catalog before go-live | ⏳ Not Started | Include department heads and process owners; capture feedback
21 | 🟡 | Publish catalog in phases starting with highest-volume items | ⏳ Not Started | Reduce risk; gather feedback before full rollout
22 | 🟢 | Announce catalog availability to end users via internal comms (email, Teams/Slack, intranet) | ⏳ Not Started | Train staff to use the catalog instead of sending ad hoc emails
23 | 🟢 | Monitor catalog usage analytics in first 30 days post-launch | ⏳ Not Started | Identify unused items, high-abandonment forms, or misrouted requests
5.5 Employee Onboarding & Offboarding Workflows
24 | 🟡 | Define onboarding workflow: tasks by role, department, required provisioning steps, approvals | ⏳ Not Started | Involve HR, IT, Facilities, and Security in requirements
25 | 🟡 | Configure onboarding request form and task templates in Freshservice | ⏳ Not Started | Admin > Employee Journeys > Onboarding
26 | 🟡 | Define offboarding workflow: asset return, access revocation, account deactivation, exit survey | ⏳ Not Started | Ensure security and compliance requirements are captured
27 | 🟡 | Configure offboarding request form and task templates in Freshservice | ⏳ Not Started | Admin > Employee Journeys > Offboarding
28 | 🟢 | Test end-to-end onboarding and offboarding flows with a mock new hire and departure scenario | ⏳ Not Started | Verify all tasks are created and assigned to correct groups

## 6 – Automation
Freshservice Implementation – 6 – Automation
# | Priority | Task / Action Item | Status | Notes / Owner
6.1 Workflow Automator
1 | 🔴 | Identify all automation use cases from discovery (auto-assign, approvals, notifications, child ticket creation) | ⏳ Not Started | Prioritize top 8–10 workflows for initial configuration
2 | 🔴 | Build each workflow: define Event, Conditions, and Actions clearly | ⏳ Not Started | Admin > [Workspace] > Workflow Automator; add meaningful name and description
3 | 🔴 | Add a paragraph-length description to every workflow explaining its purpose, trigger, and expected output | ⏳ Not Started | Future admins must understand the workflow without reverse engineering it
4 | 🟡 | Build auto-assignment workflows: route tickets to correct group based on category, keyword, or custom field | ⏳ Not Started | Example: Category = VPN → Assign to Network Ops group
5 | 🟡 | Build approval-triggering workflows for catalog items or change requests requiring sign-off | ⏳ Not Started | Include conditions for cost thresholds, requester type, or asset category
6 | 🟡 | Build task-creation workflows: auto-generate child tasks when a service request is approved | ⏳ Not Started | Example: Approved laptop request → creates Procurement, Config, Delivery tasks
7 | 🟡 | Build notification workflows for escalations, SLA warnings, and team alerts | ⏳ Not Started | Avoid over-notifying; target specific roles or thresholds
8 | 🟡 | Build onboarding/offboarding orchestration workflows spanning IT, HR, and Facilities | ⏳ Not Started | Multi-step, multi-group workflows requiring careful dependency mapping
9 | 🟢 | Document every workflow in a central automation inventory (JSON export + description) | ⏳ Not Started | Freshservice does not have native export; maintain manually in a spreadsheet or JSON file
10 | 🟢 | Test all workflows with test tickets covering both positive and edge case scenarios | ⏳ Not Started | Verify conditions are working as expected; check execution logs
11 | 🟢 | Deactivate or archive any unused or placeholder workflows before go-live | ⏳ Not Started | Clean automation list reduces confusion and debug time
6.2 Business Rules
12 | 🟡 | Define business rules for conditional form behavior (show/hide fields, make fields mandatory based on values) | 🔄 In Progress | Admin > [Workspace] > Business Rules; runs client-side on ticket forms
13 | 🟡 | Test business rules across different ticket types and user roles | ⏳ Not Started | Business rules behave differently from Workflow Automator – test separately
6.3 Supervisor Rules
14 | 🟡 | Create supervisor rules for time-based escalations (e.g., escalate unassigned tickets after 2 hours) | ⏳ Not Started | Admin > [Workspace] > Supervisor Rules; runs on a schedule
15 | 🟡 | Create supervisor rules for follow-up actions on pending or SLA-approaching tickets | ⏳ Not Started | Example: Send reminder after 24 hours if ticket remains in 'Pending Customer' status
16 | 🟢 | Document all supervisor rules including schedule frequency and escalation targets | ⏳ Not Started | Avoid duplicating logic already in Workflow Automator
6.4 Scenario Automations
17 | 🟡 | Create scenario automations for common manual agent actions (e.g., 'Assign to Networking', 'Escalate to Manager') | ⏳ Not Started | Admin > [Workspace] > Scenario Automation; agents execute manually with one click
18 | 🟢 | Train agents on how to find and execute scenario automations from the ticket detail screen | ⏳ Not Started | Include in agent training materials
6.5 Scheduler
19 | 🟢 | Configure scheduled automations for recurring tasks (weekly reports, SLA summary, ticket cleanup) | ⏳ Not Started | Admin > [Workspace] > Scheduler
20 | 🟢 | Document scheduler frequency, actions, and responsible owner for each scheduled task | ⏳ Not Started
6.6 Orchestration Center
21 | 🟢 | Identify integration use cases that require orchestration (e.g., Active Directory user provisioning, Jira ticket sync) | ⏳ Not Started | Admin > Orchestration Center; requires Enterprise plan
22 | 🟢 | Configure credentials for each orchestration target and test connectivity | ⏳ Not Started | Admin > Orchestration Center > Credentials
23 | 🟢 | Build and test orchestration workflows for approved integration use cases | ⏳ Not Started | Test in sandbox before deploying to production

## 7 – ITSM Modules
Freshservice Implementation – 7 – ITSM Modules
# | Priority | Task / Action Item | Status | Notes / Owner
7.1 Incident Management
1 | 🔴 | Configure incident categories, subcategories, and items based on discovery outputs | ⏳ Not Started | Align with common ticket types observed in legacy system data
2 | 🔴 | Define incident priority matrix (Urgency + Impact = Priority) and configure in Freshservice | ⏳ Not Started | Admin > [Workspace] > Priority Matrix
3 | 🔴 | Configure major incident type field and promotion logic (when is an incident promoted to Major Incident?) | ⏳ Not Started | Major Incident fields: Type, Business Impact, Impacted Locations, Customer Count
4 | 🟡 | Set up On-Call schedules for critical incident coverage outside business hours | ⏳ Not Started | Admin > [Workspace] > On-Call Schedules; define escalation rotations
5 | 🟡 | Configure Post-Incident Report (PIR) templates for major incidents | ⏳ Not Started | Admin > [Workspace] > Post-Incident Report Templates
6 | 🟡 | Configure status page settings for broadcasting major incidents to internal and external stakeholders | ⏳ Not Started | Admin > Global Settings > Status Page Settings
7 | 🟢 | Configure related-ticket linking behavior (parent-child for major incidents) | ⏳ Not Started | Note: parent-child merge cannot be undone in Freshservice
7.2 Problem Management
8 | 🟡 | Configure problem ticket form with root cause, impact analysis, and workaround fields | ⏳ Not Started | Admin > [Workspace] > Problem Fields
9 | 🟡 | Define the process for linking incidents to problems and escalating from Incident to Problem | ⏳ Not Started | Train agents on when to raise a Problem vs. keep an Incident open
10 | 🟢 | Create problem review workflow: who reviews, approves, and closes problems? | ⏳ Not Started | Align with ITIL Problem Management practice
7.3 Change Management
11 | 🔴 | Define change types for the organization: Standard, Normal, Emergency | ⏳ Not Started | Align with discovery session outputs and CAB structure
12 | 🔴 | Configure Change Advisory Board (CAB) approval groups and workflows | ⏳ Not Started | Define who approves each change type; configure in Workflow Automator
13 | 🔴 | Configure change lifecycle statuses and transitions | ⏳ Not Started | Admin > [Workspace] > Change Statuses; map to ITIL change lifecycle
14 | 🟡 | Build change request form with all required fields: risk, impact, rollback plan, affected services | ⏳ Not Started | Admin > [Workspace] > Change Fields
15 | 🟡 | Configure change calendar and scheduling fields (planned start, end, downtime window) | ⏳ Not Started | Integrate with change workflow for scheduling visibility
16 | 🟡 | Create change notification workflows: notify CAB, approvers, stakeholders at each lifecycle stage | ⏳ Not Started | Include rejection and withdrawal workflows
17 | 🟢 | Configure document templates for change records (e.g., Change Request, Test Plan, Communication) | ⏳ Not Started | Admin > [Workspace] > Document Templates
18 | 🟢 | Define and configure the Forward Schedule of Changes (FSC) view for CAB meetings | ⏳ Not Started | Use change calendar or custom view for weekly CAB review
7.4 Release Management
19 | 🟡 | Configure release types (Major, Minor, Emergency) and lifecycle statuses | ⏳ Not Started | Admin > [Workspace] > Release Statuses
20 | 🟡 | Build release request form with deployment plan, rollback plan, and affected CIs | ⏳ Not Started | Admin > [Workspace] > Release Fields
21 | 🟢 | Link release management workflow to change management for coordinated deployments | ⏳ Not Started | Releases should be associated with approved Change records
7.5 Tasks
22 | 🟡 | Define task types used across the organization (Technical, Approval, Coordination, Verification) | ⏳ Not Started | Admin > [Workspace] > Task Types
23 | 🟡 | Configure task templates for common multi-step fulfillment workflows (e.g., New Hire IT Kit) | ⏳ Not Started | Tasks can be auto-created via Workflow Automator
24 | 🟢 | Configure Finish-to-Start task dependencies for ordered task sequences | ⏳ Not Started | Prevents later tasks from being completed before prior tasks are done

## 8 – Asset & CMDB
Freshservice Implementation – 8 – Asset & CMDB
# | Priority | Task / Action Item | Status | Notes / Owner
8.1 Asset Types & Fields
1 | 🔴 | Define asset types to be tracked (Laptop, Desktop, Monitor, Server, Mobile, Network Device, Printer, License) | ⏳ Not Started | Admin > Asset Types & Fields; model to match real inventory
2 | 🔴 | Create custom asset fields for each asset type (Serial Number, Warranty Date, Location, Assigned User, etc.) | ⏳ Not Started | Admin > Asset Types & Fields; align with physical asset tags and procurement data
3 | 🟡 | Define asset lifecycle states (In Stock, In Use, In Repair, Retired, Disposed) | ⏳ Not Started | Confirm lifecycle stages with IT operations team
4 | 🟡 | Configure asset relationship types to support CMDB (depends on, connected to, installed on, etc.) | ⏳ Not Started | Admin > Global Settings > Relationship Types
5 | 🟢 | Configure asset depreciation rules and schedules by asset type | ⏳ Not Started | Admin > Global Settings > Asset Depreciation
8.2 CMDB Configuration
6 | 🔴 | Define CMDB scope: which CIs (Configuration Items) will be tracked beyond physical assets (Services, Applications, VMs, etc.) | ⏳ Not Started | Align with Change and Incident Management processes
7 | 🟡 | Import initial asset inventory via CSV or discovery tool | ⏳ Not Started | Clean data before import; validate required fields
8 | 🟡 | Configure Discovery Hub or integrate with a discovery tool (JAMF, SCCM, Lansweeper, etc.) for automated asset discovery | ⏳ Not Started | Admin > Discovery Hub; or use Freshservice agent/probe for network discovery
9 | 🟡 | Link CIs to related incidents, changes, and service requests | ⏳ Not Started | Establishes traceability and CMDB value in daily operations
10 | 🟢 | Set up cloud asset management integration (AWS, Azure, GCP) if applicable | ⏳ Not Started | Admin > Cloud Management
8.3 Software Asset Management
11 | 🟡 | Configure software asset types and fields (Vendor, License Type, Seats, Expiry Date, Cost) | ⏳ Not Started | Admin > Software Fields
12 | 🟡 | Import or sync software inventory from discovery tools or CSV | ⏳ Not Started | Admin > Inventory > Software
13 | 🟡 | Configure SaaS management tracking if applicable (cloud app discovery and spend optimization) | ⏳ Not Started | Admin > SaaS Management
14 | 🟢 | Set up software license compliance alerts for over/under-allocation | ⏳ Not Started | Align with compliance and procurement teams
8.4 Contracts & Purchase Orders
15 | 🟡 | Configure contract fields: vendor, type, value, start/end dates, renewal terms | ⏳ Not Started | Admin > Managing Contract Fields
16 | 🟡 | Import existing vendor contracts and link to associated assets or services | ⏳ Not Started | Admin > Inventory > Contracts
17 | 🟡 | Configure purchase order fields and workflow (requestor, approver, fulfillment tracking) | ⏳ Not Started | Admin > Inventory > Purchase Orders
18 | 🟢 | Set contract renewal alerts (e.g., 90/60/30 days before expiry) | ⏳ Not Started | Use Supervisor Rules or Workflow Automator to trigger alerts
8.5 Vendor Management
19 | 🟢 | Configure vendor fields and create vendor records for key IT and service vendors | ⏳ Not Started | Admin > Vendor Fields; Admin > Vendor Management
20 | 🟢 | Link vendors to associated contracts, assets, and purchase orders | ⏳ Not Started | Enables centralized supplier directory in Freshservice

## 9 – AI & Channels
Freshservice Implementation – 9 – AI & Channels
# | Priority | Task / Action Item | Status | Notes / Owner
9.1 Freddy AI Configuration
1 | 🔴 | Confirm which Freddy AI modules are included in the plan: Freddy AI Agent, Freddy AI Copilot, Freddy AI Insights | ⏳ Not Started | Admin > Plans & Billing > Activate Add-ons; verify per-agent licensing
2 | 🟡 | Enable Freddy AI Copilot for eligible agents: configure access in Plans & Billing | ⏳ Not Started | Copilot provides: suggested replies, ticket summaries, article drafts
3 | 🟡 | Enable Freddy AI Insights: configure access for IT managers and service desk leads | ⏳ Not Started | Insights provides: trend analysis, root cause recommendations, performance reports
4 | 🟡 | Review and confirm that business hours, time zones, and SLA settings are accurate (Freddy relies on these for correct analytics) | ⏳ Not Started | Misconfigured time settings distort Freddy's SLA and workload insights
5 | 🟡 | Confirm SPF/DKIM email authentication is in place (required for Freddy-generated email communications) | ⏳ Not Started | Freddy-generated notifications must pass email authentication to reach users
6 | 🟢 | Train agents on how to use Freddy Copilot suggestions: when to accept, modify, or override AI responses | ⏳ Not Started | Include in agent training curriculum
7 | 🟢 | Review Freddy Insights dashboard after 2–4 weeks post-launch to validate data accuracy | ⏳ Not Started | Freddy improves as it ingests more ticket data
9.2 Freddy AI Agent (Chatbot / Servicebot)
8 | 🟡 | Enable the Servicebot (Freddy AI Agent) for the self-service portal and/or collaboration tools | ⏳ Not Started | Admin > Global Settings > Channels > Servicebot
9 | 🟡 | Connect Freddy AI Agent to Microsoft Teams and/or Slack as applicable | ⏳ Not Started | Admin > Global Settings > Channels > Microsoft Teams / Slack
10 | 🟡 | Configure bot greeting, persona, and fallback behavior when AI cannot resolve the query | ⏳ Not Started | Fallback should route to a human agent gracefully
11 | 🟡 | Train the bot by linking it to the knowledge base; ensure articles are published and categorized | ⏳ Not Started | Bot effectiveness is directly tied to KB article quality
12 | 🟢 | Test chatbot across common query types from discovery (password reset, VPN, equipment request, etc.) | ⏳ Not Started | Validate bot deflection rate before go-live announcement
9.3 Microsoft Teams & Slack Integration
13 | 🟡 | Install the Freshservice app in Microsoft Teams or Slack from the marketplace | ⏳ Not Started | Admin > Global Settings > Channels; follow Freshservice setup guide
14 | 🟡 | Configure notification routing: which Teams channels or Slack channels receive ticket alerts? | ⏳ Not Started | Avoid channel noise; route only critical or relevant notifications
15 | 🟡 | Test ticket creation, update notifications, and bot interactions via Teams/Slack | ⏳ Not Started | Verify the experience matches expectations from discovery
16 | 🟢 | Communicate Teams/Slack integration availability to all agents and end users | ⏳ Not Started | Include in go-live announcement and training materials
9.4 Additional Channels & Marketplace Apps
17 | 🟡 | Review the Freshservice App Marketplace for integration apps aligned to the project scope (Jira, ServiceNow, AD, monitoring tools, etc.) | ⏳ Not Started | Admin > App Marketplace; shortlist apps identified during discovery
18 | 🟡 | Install and configure approved marketplace apps and test in sandbox before production deployment | ⏳ Not Started | Validate each app integration end-to-end with test data
19 | 🟢 | Configure walk-up support channel if applicable (physical kiosk or in-person request intake) | ⏳ Not Started | Admin > [Workspace] > Channels > Walk-up
20 | 🟢 | Configure Leaderboard and agent gamification settings if desired for agent engagement | ⏳ Not Started | Admin > [Workspace] > Leaderboard; configure points, badges, and tiers

## 10 – Knowledge & Reporting
Freshservice Implementation – 10 – Knowledge & Reporting
# | Priority | Task / Action Item | Status | Notes / Owner
10.1 Knowledge Base Setup
1 | 🔴 | Plan knowledge base structure: folders and sub-folders aligned to ticket categories and user audience | ⏳ Not Started | Separate agent-only content from requester-visible content
2 | 🔴 | Migrate or create initial set of knowledge articles (minimum 10–20 high-value articles for go-live) | ⏳ Not Started | Focus on top 10 most common ticket types identified in discovery
3 | 🔴 | Configure knowledge base visibility: which articles are public, internal (agent-only), or department-restricted | ⏳ Not Started | Align visibility with requester groups and service catalog items
4 | 🟡 | Add keywords and tags to all articles for improved search relevance | ⏳ Not Started | Distinguish between tags (filtering) and keywords (search optimization)
5 | 🟡 | Link knowledge articles to relevant catalog items and ticket categories | ⏳ Not Started | Enables article suggestion in ticket reply and Freddy Copilot recommendations
6 | 🟡 | Set article review schedules and assign article owners for ongoing maintenance | ⏳ Not Started | Stale knowledge base articles reduce self-service adoption
7 | 🟢 | Enable article approval workflow if articles must be reviewed before publishing | ⏳ Not Started | Ensures quality control for public-facing content
8 | 🟢 | Encourage agents to create solution articles from resolved tickets during hypercare period | ⏳ Not Started | Leverage closure notes and resolutions as drafts for KB articles
10.2 Reports & Dashboards
9 | 🔴 | Identify key reports required from discovery: SLA compliance, ticket volume, agent performance, resolution time by category | ⏳ Not Started | Document specific metrics and required time ranges per report
10 | 🔴 | Build core reports for each key stakeholder group: IT Manager, Service Desk Lead, Executive Summary | ⏳ Not Started | Admin > Reports; use built-in report templates as starting points
11 | 🟡 | Configure custom dashboards with key widgets: open tickets, SLA breaches, agent performance, satisfaction score | ⏳ Not Started | Customize dashboards per role; share with appropriate user groups
12 | 🟡 | Configure workspace-specific reports for HR, Facilities, Finance, and other non-IT workspaces | ⏳ Not Started | Ensure each department head can see their own service metrics
13 | 🟡 | Set up scheduled report delivery (weekly/monthly email to stakeholders) | ⏳ Not Started | Reduces manual reporting effort; keeps leadership informed
14 | 🟢 | Enable Freddy AI Insights dashboards for proactive service analytics after 2–4 weeks of data | ⏳ Not Started | Freddy Insights requires ticket data history to generate meaningful trends
15 | 🟢 | Configure project analytics reports if Freshservice Projects module is in scope | ⏳ Not Started | Admin > Project Analytics

## 11 – Go-Live & Hypercare
Freshservice Implementation – 11 – Go-Live & Hypercare
# | Priority | Task / Action Item | Status | Notes / Owner
11.1 Agent Training
1 | 🔴 | Develop agent training curriculum: ticket management, catalog items, groups, views, canned responses, Freddy Copilot | ⏳ Not Started | Customize to each agent's role and workspace
2 | 🔴 | Conduct live training sessions (or record video walkthroughs) for all agent groups before go-live | ⏳ Not Started | Hands-on training in sandbox is most effective
3 | 🟡 | Create quick-reference guides for common agent tasks (creating tickets, running reports, using KB) | ⏳ Not Started | Share in Teams/Slack and include in knowledge base
4 | 🟡 | Train agents on Freshservice mobile app usage if applicable | ⏳ Not Started | Especially important for facilities or on-site support teams
5 | 🟢 | Document escalation paths and ITIL process ownership for agents to reference post-go-live | ⏳ Not Started
11.2 End-User / Requester Training
6 | 🔴 | Develop end-user communication plan: announce the new portal, explain how to submit requests | ⏳ Not Started | Use email, intranet, Teams/Slack announcements
7 | 🟡 | Create a short end-user guide: how to log in, submit a ticket, check status, use the catalog | ⏳ Not Started | Keep it visual and under 1 page; link from the portal landing page
8 | 🟡 | Host a 'launch day' town hall or walkthrough demo for all employees | ⏳ Not Started | Optional but strongly increases early adoption
9 | 🟢 | Add onboarding banner or welcome message on the requester portal for the first 30 days | ⏳ Not Started | Guides first-time users; reduces misdirected tickets
11.3 User Acceptance Testing (UAT)
10 | 🔴 | Develop UAT test plan with test scenarios covering all in-scope features (tickets, catalog, approvals, automations, reports) | ⏳ Not Started | Include both happy path and edge case scenarios
11 | 🔴 | Conduct UAT with representative users from each department (agents and requesters) | ⏳ Not Started | Capture all defects and enhancement requests in a UAT tracker
12 | 🔴 | Resolve all critical UAT defects before go-live; document accepted workarounds for non-critical issues | ⏳ Not Started | Define go/no-go criteria based on severity of open issues
13 | 🟡 | Obtain formal UAT sign-off from project sponsor and key stakeholders | ⏳ Not Started | Document approval for governance and project closure records
11.4 Go-Live Readiness & Execution
14 | 🔴 | Complete a pre-go-live checklist: all agents trained, portal branded, SLAs active, catalog published, automations tested | ⏳ Not Started | Review against this checklist in the 48 hours before launch
15 | 🔴 | Remove the 'Under Construction' login banner and confirm the portal is publicly accessible | ⏳ Not Started | Verify from multiple user accounts and browsers
16 | 🔴 | Monitor ticket creation, routing, and SLA behavior closely on day 1 and day 2 | ⏳ Not Started | Have the implementation team on standby for rapid issue resolution
17 | 🟡 | Disable old ticketing system intake channels (shared mailboxes, legacy portals) and redirect to Freshservice | ⏳ Not Started | Coordinate with IT and communications team on cutover timing
18 | 🟡 | Confirm email routing is fully live: all support inboxes are forwarding to Freshservice mailboxes | ⏳ Not Started | Send test emails from multiple domains; verify ticket creation and replies
19 | 🟢 | Send go-live announcement to all employees with portal URL, how-to guide, and support contact | ⏳ Not Started | Include FAQ for common first-day questions
11.5 Hypercare Period (Days 1–30 Post Go-Live)
20 | 🔴 | Maintain heightened monitoring of ticket queues, SLA performance, and automation behavior for first 30 days | ⏳ Not Started | Hold daily stand-ups in the first week; weekly in weeks 2–4
21 | 🔴 | Address all critical issues (wrong routing, broken automations, access problems) within 24 hours | ⏳ Not Started | Escalate to Freshservice support if needed; document all issues and resolutions
22 | 🟡 | Collect feedback from agents and end users via survey or open feedback channel | ⏳ Not Started | Use feedback to prioritize Phase 2 backlog
23 | 🟡 | Review knowledge base usage and article feedback; create new articles for common questions from helpdesk | ⏳ Not Started | Aim to resolve the top 5 recurring ticket types with self-service articles
24 | 🟢 | Begin compiling lessons learned and implementation retrospective notes | ⏳ Not Started | Used for post-implementation review and future project planning
11.6 Post-Implementation Review & Handoff
25 | 🔴 | Conduct formal Post-Implementation Review (PIR): what went well, what to improve, remaining risks | ⏳ Not Started | Invite all stakeholders; document outcomes in the RAID log
26 | 🔴 | Transition ownership to the internal Freshservice administrator(s); provide full system documentation | ⏳ Not Started | Handoff package should include: configuration workbook, automation inventory, role matrix, SLA register, and KB article list
27 | 🟡 | Create and share an Internal Admin Guide covering all key configurations and how to maintain them | ⏳ Not Started | Reference 'Mastering Freshservice Implementations' for ongoing administrative guidance
28 | 🟡 | Define and document the ongoing governance model: who owns changes to workflows, catalog, roles, and KB? | ⏳ Not Started | Prevents configuration drift and ensures accountability post-handoff
29 | 🟡 | Schedule Phase 2 kickoff to address backlog items identified during implementation and hypercare | ⏳ Not Started | Prioritize by business impact and user demand
30 | 🟢 | Schedule a 90-day and 180-day health check review to assess platform adoption and SLA performance | ⏳ Not Started | Tie to Freshservice success metrics established during discovery
31 | 🟢 | Recommend ongoing use of Freshservice Audit Log for change tracking and compliance | ⏳ Not Started | Admin > Global Settings > Audit Log